## Slide 1: Software Project Scope Management

## Slide 2: Review
What is the project charter?
  The project charter is the first document that exists in the project.
  It causes the project to come into existence.
  The project charter names the project and briefly describes it.
  It names the project manager and causes a cost account to be opened to capture the cost of the project.
  Once these essential things have been done, work on the project can proceed.
  The project charter is written by the project sponsor, or some senior executive and signed by all relevant stakeholders.

## Slide 3
The Project charter is created by:
  The project manager
  Upper management
  The Vice President over a functional management group

## Slide 4: Who needs software?
Most software is built in organizations for people with specific needs.
  A stakeholder is anyone who has an interest (or stake) in the software being completed
  A user is someone who will need to use the software to perform tasks.
  Sometimes stakeholders will be users; but often the stakeholder will not use the software.
    For example, a senior manager (like a CEO in a company) will usually have a stake in the software that is built, even if they won’t ever use it.

## Slide 5: Who builds software?
Software is typically built by a team of software engineers, which includes:
  Business analysts or requirements analysts:
    Talk to users and stakeholders, plan the behavior of software and write software requirements
  Designers and architects:
    Plan the technical solution
  Programmers:
    write the code
  Testers:
    Verify that the software meets its requirements and behaves as expected

## Slide 6: Project Generator
Business need
Market demand
Customer request
Legal requirement
Technological advance
Social need
Project

## Slide 7: Project initiation
Project Requests
Project 1
Project 2
Project 3
Project n
Project Selection & Prioritization
Request for Project (Document)
payback period
Cost-benefit analysis
IRR
ROI
Strategic Plan
Risks and Impact
Constraints
Feasibility Study
Meeting with Stakeholders
Working with Project Sponsor
Pre Project Phase
Project Charter
Notes: The internal rate of return (IRR) of a project is the expected growth rate of a project investment.

## Slide 8: Why - Project
Three important criteria for projects:
  There is a need for project
  There are funds available
  There’s a strong will to make project succeed
After deciding what project to work on, it’s important to formalize projects

## Slide 9: Identifying Needs
The project manager drives the scope of the project.
  The project manager should identify and talk to the main stakeholder
    what the project contains or delivers
  The effective way to show stakeholders that their needs are understood and that those specific needs will be addressed is with a vision and scope document
The Scope Statement provides a common understanding of the project among stakeholders
  Some organizations create a separate Scope Statement Document while others make it a part of the Project Charter or Project Plan.

## Slide 10: Project Scope Management?
Scope refers to all the work involved in creating the products of the project and the processes used to create them
A deliverable is a product produced as part of a project,
    such as hardware or software, planning documents, or meeting minutes
  External deliverables
    things the project delivers to the users e.g. screens and reports. Users typically think of a system in these terms. It also includes any hardware or software required by the users or the project team.
  Internal deliverables
    things the project generates internally e.g. Project Charter, Business Requirement Specification etc.
Project scope management includes
  The processes involved in defining and controlling what is or is not included in a project

## Slide 11
Scope (most critical step):
  Clearly describe the boundaries of your project and get the client's agreement as well.
  High level-scope statement (SOW (Statement of Work).
    When the project is about to be funded, a set of defined deliveries and objectives must be defined
    Project objectives can be used for defining the project scope
    Defining the out of scope also helps to understand the scope
      Document “IN” and “OUT” of Scope

## Slide 12: The knowledge area of Project Scope Management
The knowledge area of Scope Management includes the processes required to ensure that the project includes all the work, and only all the work required to complete the project successfully. It is primarily concerned with controlling what is and what is not in the scope.
Process | Project Group | Key Deliverables
Plan Scope Management | Planning | 
Collect Requirements | Planning | Requirements document
Define Scope | planning | project scope statement
Create WBS | planning | WBS, WBS dictionary
Validate Scope | Monitoring and Controlling | Acceptance deliverables
Control Scope | Monitoring and Controlling | Change Requests

## Slide 13: Potential Deliverables by Phase

## Slide 14
Each project phase is marked by completion of one or more:
  Tasks.
  Milestones
  Deliverables
  Life cycles

## Slide 15
Each project phase is marked by completion of one or more:
  Tasks.
  Milestones
  Deliverables
  Life cycles
Answer: Deliverables

## Slide 16
Deliverables are the actual product which is delivered during the project or a certain period of the project.
  It is tangible as well as verifiable.
  It must meet the original project requirements, such as specifications.
Milestones mark the accomplishment of a tangible objective of the project such, as the completion of the design phase.
  Milestones are defined in the work breakdown structure (WBS).

## Slide 17: Project Scope Management Processes
Scope planning:
  Deciding how the scope will be defined, verified, and controlled
Scope definition:
  Reviewing the project charter and preliminary scope statement and adding more information as requirements are developed and change requests are approved
Creating the WBS:
  Subdividing the major project deliverables into smaller, more manageable components
Scope verification:
  Formalizing acceptance of the project scope
Scope control:
  Controlling changes to project scope

## Slide 19: Preliminary Scope Statements
A scope statement is a document used to develop and confirm a common understanding of the project scope
It’s important for preventing scope creep
  the tendency for project scope to keep getting bigger
It’s good practice to develop a preliminary or initial scope statement during project initiation and a more detailed scope statement as the project progresses.

## Slide 20: Project scope statement
Project scope statement should include
  A description of the project
  Overall objectives and justification
  Detailed description of all project deliverables
  The characteristics and requirements of products and services

## Slide 21: Scope Management Plan
The scope management plan
  A document that includes:
    Descriptions of how the team will prepare the project scope statement,
    create the WBS,
    verify completion of the project deliverables, and
    control requests for changes to the project scope
Key inputs include:
  The project charter, preliminary scope statement, and project management plan

## Slide 22: Example

## Slide 23: Stakeholder Analysis
A stakeholder analysis documents holds important (often sensitive) information about stakeholders such as
  stakeholders’ names and organizations
  roles on the project
  unique facts about stakeholders
  level of influence and interest in the project
  suggestions for managing relationships

## Slide 24: Sample Stakeholder Analysis

## Slide 25: Stakeholder Roles and Responsibilities
Stakeholder | Responsibility
Project manager | Manages project, creates project plans, creates various management plans related to the project, measures project performance, takes corrective action, controls project outcomes, manages project team, and reports status
Project sponsor | Executive who initiates and oversees the project. Serves as an advisor to the project manager; can resolve issues and make decisions. Issues the project charter. Serves on project oversight or steering committee.
Functional managers | Responsible for completing project activities and producing deliverables. May serve on project oversight or steering committee to help oversee management of the project.
Customer | Provides project requirements. Approves project deliverables and verifies that they meet requirements. Serves on project oversight or steering committee.
Project team | Responsible for completing the activities of the project.
Suppliers | Provide goods or services to assist project team in completing project.

## Slide 26: Work Breakdown Structure: WBS
A WBS is a deliverable-oriented grouping of the work involved in a project that defines the total scope of the project
  WBS is a foundation document that provides the basis for:
    Planning and managing project schedules, costs, resources, and changes
Decomposition is subdividing project deliverables into smaller pieces

## Slide 27: Work Breakdown Structure: WBS
Hierarchical list of project’s work activities
Two Formats
  Outline (indented format)
  Graphical Tree (Organizational Chart)
Uses a decimal numbering system
  Ex: 3.1.5
  0 is typically top level

## Slide 28: WBS Chart Example

## Slide 29: WBS Types
Process WBS (a.k.a Activity-oriented)
    Ex: Requirements, Analysis, Design, Testing
    Typically used by PM
Product WBS (a.k.a. Entity-oriented)
    Ex: Interface system, DB
    Typically used by engineering manager

## Slide 30: WBS Dictionary
Many WBS tasks are ambiguous and must be explained in more detail so people know what to do and can estimate how long the work will take and what it will cost.
A WBS dictionary is a document that describes detailed information about each WBS item.
The approved project scope statement and its WBS and WBS dictionary form the scope baseline, which is used to measure performance in meeting project scope goals.

## Slide 33: Work Packages
Generic term for discrete tasks with definable end results
Typically the “leaves” on the tree
Basis for monitoring and reporting progress
Ideally shorter rather than longer
    Longer makes in-progress estimates needed
    2-3 weeks maximum for software projects
    1 day minimum (occasionally a half day)

## Slide 34: WBS Techniques
Top-down
  Start at highest level
  Systematically develop increasing level of detail
  Best if
    The problem is well understood
    Technology and methodology are not new
    This is similar to an earlier project or problem
  But is also applied in majority of situations
Bottom-up
  Start at lowest level tasks
  Cons
    Time consuming
    Needs more requirements complete
  Pros
    Detailed

## Slide 35: WBS Techniques
Analogy
  Base WBS upon a “similar” project
  Use a template
  Pros
    Based on past actual experience
  Cons
    Needs comparable project
Notes: Review WBSs of similar projects and tailor to your project.

## Slide 36: WBS Techniques
Brainstorming
  Generate all activities you can think of that need to be done
  Group them into categories
Both Top-down and Brainstorming can be used on the same WBS

## Slide 37: WBS – Basis of Many Things
Network scheduling
Costing
Risk analysis
Organizational structure
Control
Measurement
Notes: Organizational structure is a way or method by which. organizational activities are divided, organized and coordinated. The organizations created the structures to coordinate the. activities of work factors and control the member performance

## Slide 38: Causes of Scope Creep
Scope creep is scope keep getting bigger and bigger
Poor WBS
Underestimating the Complexity of the Project
  Over budget and over time
Lack of Change Control
Notes: Scope creep is what happens when changes are made to the project scope without any control procedure like change requests. Those changes also affect the project schedule, budget, costs, resource allocation and might compromise the completion of milestones and goals

## Slide 39: Scope Verification
Scope verification involves formal acceptance of the completed project scope by the stakeholder
Careful procedures must be developed to ensure the customer is getting what they want, and the project team has enough time and money to produce the desired products and services

## Slide 40: Scope control
Scope control involves controlling changes to the project scope.
Goals of scope control are to:
  Ensure changes are processed according to procedures developed as part of integrated change control.
  Manage changes when they occur.
  Variance is the difference between planned and actual performance.